## Instructions
Sprint Planning — Instructions & Legend
COSC2408 Programming Project 1
What this workbook is for
This is the detailed HOW for next sprint — the task-by-task breakdown, owner, timing and sequencing. It is a separate deliverable from your Sprint Playback slide 7 ("What's Next"), which only states WHAT you're promising. This workbook is where that promise gets broken down into real, assigned, time-estimated tasks.
The 240-minute rule
Every team member must be assigned at least 240 minutes (4 hours) of tasks per week, for every week of the upcoming sprint. Estimate time at a junior-practitioner level — the same standard used for your weekly task board (e.g. a straightforward API endpoint with tests is ~30 minutes, regardless of how long it actually takes you in practice). The Weekly Workload Check tab totals this automatically and flags anyone under the minimum.
How to use the Task Plan & Gantt tab
1. Delete the yellow example row once you understand the format — it is not a real task.
2. Add one row per task: name it, assign an Owner, estimate the minutes, set the Week (1–3), the Start Day WITHIN that week (1 = Monday, 5 = Friday) and the Duration in days.
3. The Gantt bar on the right fills in automatically based on Start Day and Duration — you don't edit it directly.
4. Use Dependencies to note if a task can't start until another Task ID is done.
5. Update Status as the sprint progresses — this tab doubles as your working plan, not just a one-off submission.
Editable vs computed
Only the white cells in the Task Plan & Gantt tab are for you to fill in (Task ID through Status). The Gantt bars and everything on the Weekly Workload Check tab are computed automatically — don't type into them. You can change the roles by maunally typing into Column C (owner) and then using the same valueein the Weekly Workload check
Submission
Rename this file x - team name - S1W7_ganttplan (e.g. 90 - Food Delivery System - S1W7_ganttplan) and submit alongside your other Week 7 files. It plans the upcoming sprint, so it's due the same week as your Playback.
Colour key
Example row — delete before submitting
Weekly Workload Check: meets the 240-minute minimum
Weekly Workload Check: under the 240-minute minimum

## Task Plan & Gantt
Team 26 — Next-Sprint Task Plan & Gantt ¦ Sprint 2 (Weeks 4–6)
Every member needs ≥240 min/week. See the Instructions tab before editing.
Task ID | Task Name | Owner | Est. Minutes | Week | Start Day (1=Mon–5=Fri) | Duration (days) | Dependencies | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
[8 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
T1 | Sprint 2 Planning & Group Allignment | PM | 120 | 1 | 1 | 3 | -
T2 | Establish Sprint Tracking & Risk Management | PM | 180 | 1 | 3 | 3 | -
T3 | Organise & Run Weekly Team Meeting | PM | 120 | 1 | 1 | 2 | -
T4 | Finalise Prototype Requirements & Acceptance Criteria | Business/QA | 180 | 1 | 1 | 3 | -
T5 | Finalise Proposed User Journey | Business/QA | 120 | 1 | 3 | 3 | T1
T6 | Attend Weekly Team Meeting | Business/QA | 60 | 1 | 2 | 1 | -
T7 | Finalise Prototype User Flow & Wireframes | UX/Research | 180 | 1 | 1 | 3 | -
T8 | Prepare Developer-Ready UX Specification | UX/Research | 180 | 1 | 3 | 3 | T4
T9 | Attend Weekly Team Meeting | UX/Research | 60 | 1 | 2 | 1 | -
T10 | Design Prototype Technical Workflow & Application Structure | Dev 1 | 180 | 1 | 1 | 3 | -
T11 | Begin Prototype Development | Dev 1 | 180 | 1 | 3 | 3 | T7 & T10
T12 | Attend Weekly Team Meeting | Dev 1 | 60 | 1 | 2 | 1 | -
T13 | Design Prototype Technical Workflow & Application Structure | Dev 2 | 180 | 1 | 1 | 3 | -
T14 | Begin Prototype Development | Dev 2 | 180 | 1 | 3 | 3 | T7 & T10
T15 | Attend Weekly Team Meeting | Dev 2 | 60 | 1 | 2 | 1 | -
T16 | Conduct Mid-Sprint Progress & Scope Review | PM | 120 | 2 | 1 | 3 | T8 & T11
T17 | Coordinate Prototype Integration & Resolve Blockers | PM | 120 | 2 | 3 | 3 | T8 & T11
T18 | Organise & Run Weekly Team Meeting | PM | 120 | 2 | 1 | 2 | -
T19 | Develop Prototype Test Scenarios | Business/QA | 180 | 2 | 1 | 3 | T4
T20 | Conduct Mid-Sprint Client Requirements Review | Business/QA | 180 | 2 | 3 | 3 | T13
T21 | Attend Weekly Team Meeting | Business/QA | 60 | 2 | 2 | 1 | -
T22 | Check Prototype UX Implementation Progress | UX/Research | 120 | 2 | 1 | 3 | T8 & T11
T23 | Conduct Mid-Sprint Client Requirements Review | UX/Research | 180 | 2 | 3 | 3 | T16
T24 | Attend Weekly Team Meeting | UX/Research | 60 | 2 | 2 | 1 | -
T25 | Implement Vendor Form Experience | Dev 1 | 240 | 2 | 1 | 3 | T8 & T11
T26 | Implement Navigation & System Feedback | Dev 1 | 120 | 2 | 3 | 3 | T19
T27 | Attend Weekly Team Meeting | Dev 1 | 60 | 2 | 2 | 1 | -
T28 | Implement Vendor Form Experience | Dev 2 | 240 | 2 | 1 | 3 | T8 & T11
T29 | Implement Navigation & System Feedback | Dev 2 | 120 | 2 | 3 | 3 | T22
T30 | Attend Weekly Team Meeting | Dev 2 | 60 | 2 | 2 | 1 | -
T31 | Review Prototype Readiness & Sprint Close-Out | PM | 180 | 3 | 1 | 3 | T20 & T23
T32 | Prepare & Coordinate Sprint Playback | PM | 120 | 3 | 3 | 3 | -
T33 | Organise & Run Weekly Team Meeting | PM | 120 | 3 | 1 | 2 | -
T34 | Conduct Prototype Acceptance Criteria Testing | Business/QA | 180 | 3 | 1 | 3 | T20 & T23
T35 | Document Prototype Test Results, Limitations & Improvements | Business/QA | 120 | 3 | 3 | 3 | T25
T36 | Attend Weekly Team Meeting | Business/QA | 60 | 3 | 2 | 1 | -
T37 | Conduct Prototype End-to-End UX Review | UX/Research | 120 | 3 | 1 | 3 | T20 & T23
T38 | Revise Developer-Ready UX Specifications | UX/Research | 180 | 3 | 3 | 3 | T28
T39 | Attend Weekly Team Meeting | UX/Research | 60 | 3 | 2 | 1 | -
T40 | Review BA Testing & UX Prototype Notes | Dev 1 | 120 | 3 | 1 | 3 | T35 & T38
T41 | Resolve Prototype Flaws & Defects | Dev 1 | 120 | 3 | 3 | 3 | T31
T42 | Attend Weekly Team Meeting | Dev 1 | 60 | 3 | 2 | 1 | -
T43 | Test Prototype Satisfies Revised UX Requirements | Dev 2 | 120 | 3 | 1 | 3 | T31
T44 | Resolve Prototype Flaws & Defects | Dev 2 | 120 | 3 | 3 | 3 | T34
T45 | Attend Weekly Team Meeting | Dev 2 | 60 | 3 | 2 | 1 | -

## Weekly Workload Check
Weekly Workload Check — 240 min (4 hrs) minimum per person, per week
Computed automatically from the Task Plan & Gantt tab. Do not edit the numbers directly.
Role | Week 1 (min) | Week 2 (min) | Week 3 (min) | Sprint Total (min) | Sprint Total (hrs)
PM | 420 | 360 | 420 | 1200 | 20
Dev 1 | 420 | 420 | 300 | 1140 | 19
Dev 2 | 420 | 420 | 300 | 1140 | 19
UX/Research | 420 | 360 | 360 | 1140 | 19
Business/QA | 360 | 420 | 360 | 1140 | 19
Green = meets the 240-minute weekly minimum. Red = under the minimum — rebalance tasks in the Task Plan & Gantt tab.