## Plan
Plan ID | Plan name | Date of export
hSQsFu23JkuYw8GSyeqaFcgAFveM | Week 4 - project : Team 26 | 2026-09-13

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
-kEG1Tw5QEq1HHQtU_SP2cgAHzYq | Labels | Documents & Updates |  | Not started | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false
QSNHFzIY10qLVtJOZgBi7sgAB-Ov | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | Sprint 0 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-14 | Anas Rizwan | 4/5 | Edge cases documented;Login scope explicitly stated as styling-only;Document updated;Team page fields listed with validation/display rules;Requirements shared with PM and UX | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Login Restyling.docx
iXpQpvrZFUum7UVNVVMRDMgACx9R | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | Sprint 0 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-15 | Tianxiang Hang | 5/5 | Visual consistency between the two checked;Team page mockup complete;Login page mockup complete;Design shared with BA for validation;Document Updated | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task documentDocument.docx
VYcC9FH77UmvYSYtuMYj3cgAKN3_ | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Sprint 0 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 5/5 | Design formally approved;Login scope confirmed unchanged;Every required field checked against the design;Gaps (if any) sent back to UX and resolved;Document Updated | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx
iiLGTM8HakKeTcdPq6tAHMgAKslD | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Sprint 0 |  | Completed | Medium | Gabriel Halvarsson | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 4/4 | Visual style matches approved mockup;No authentication logic changed;Existing login validation/errors still function as before;Update document | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. Update master document.
zgPuuIxcbEGc8USZQpwqMMgAB9en | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Sprint 0 |  | Completed | Medium | Gabriel Halvarsson;Joel Waterhouse | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 4/4 | Document updated;Team page renders per design with all required fields;Team page not directly accessible without login;Successful login redirects to team page | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update master document.
8IiRF3sthUCIj2fqQUgI8sgAF08p | [BOOTSTRAP RESTYLING] - Deploy - 120 | Sprint 0 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 0/4 | Live URL loads without errors;Login → redirect → team page flow spot-checked on the deployed URL;Deployment completed via boilerplate pipeline;Document updated | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc
5Ljn_w-nBUSNwqHXp_9ut8gACRdu | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | Sprint 0 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 4/4 | Valid login tested end-to-end on deployed URL;Document updated;All required content verified correct and complete;Redirect to team page confirmed | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document
Se9IJ_trqEWlOQxtymn9a8gAB8Lc | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Sprint 0 |  | Completed | Medium | Joel Waterhouse | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 0/5 | Direct team-page access without login tested (must redirect);Update Document;Bugs logged with repro steps, or none-found confirmed;Missing-photo and long-blurb edge cases tested;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc
5udzOSOE-k6Uaon_24tvIsgAA7Yd | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Sprint 0 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-07 |  |  |  | false | 2026-08-16 | Tianxiang Hang | 3/3 | Feature reviewed end-to-end against requirements and design;All prior tasks' checklists verified complete;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off
Enz164Azd0iytZ2s-qU-TsgAD7U6 | Individual Data review - Dev | Sprint 1 Week 2 |  | Completed | Medium | Gabriel Halvarsson | Tianxiang Hang | 2026-08-16 |  |  |  | false | 2026-08-29 | Tianxiang Hang | 3/3 | Notes added to the shared document in a format the team can use for synthesis;Master document updated;Recurring pain points identified and logged | DEV | Monday.com review with focus on technical lens.
qFwEnBVd0EWNyiLLAImZEcgAFUAu | Individual Data review - Dev | Sprint 1 Week 2 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-16 |  |  |  | false | 2026-08-29 | Tianxiang Hang | 2/2 | Recurring pain points identified and logged;Notes added to the shared document in a format the team can use for synthesis | DEV | Monday.com review with focus on technical lens.
fWB-j6qaWUG3MVzTxa-Ny8gABguJ | Final Synthesis and review | Sprint 1 Week 2 |  | Completed | Medium |  | Tianxiang Hang | 2026-08-16 |  |  |  | false | 2026-08-29 | Tianxiang Hang | 0/2 | Clear statement of what "success" means for this project;Ready to inform Sprint 2 solution decisions | PM | Converge Week 1-2 findings into a clear articulation of what a successful outcome looks like, informing sprint 2 planning. PM should produce a final write up
e9NpoS1ad0C9M60modzDq8gANoPg | Explore technical feasibilities of Proposed solutions during Tech dropin | Sprint 1 Week 2 |  | Completed | Medium | Gabriel Halvarsson;Joel Waterhouse | Tianxiang Hang | 2026-08-25 |  |  |  | false | 2026-08-30 | Joel Waterhouse | 4/4 | Identify which LLM providers/APIs fit the project best;Check cost/privacy implications of LLM integration;Summarize feasibility findings;Review tech advisor's proposed LLM integration approach | DEV | Assess the technical feasibility of integrating an LLM into the platform, as proposed by the tech advisor
F3cBqLuKAUOdB1C0c1SwwMgAOSnm | [Sprint 1 Week 3] - Create a shared GitHub repository: 120 | Sprint 1 Week 3 |  | Completed | Medium | Joel Waterhouse | Joel Waterhouse | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-07 | Gabriel Halvarsson | 4/4 | Create folder hierachy for each sprint, role, artefacts, etc.;ReadMe - Completion;Set up Github Actions;Handoff to Dev 1 (Gabriel) | DEV;Sprint 1 | Handoff: Dev (Gabriel) Task reviewed and marked as completed - Gabriel
YErLUw2HaUeBcCOq9fIZesgAKi9q | [Sprint 1 Week 3] - Create technical workflow of the current implementation: 120 | Sprint 1 Week 3 |  | Completed | Medium | Joel Waterhouse | Joel Waterhouse | 2026-09-07 | 2026-09-12 | 2026-09-07 |  | false | 2026-09-11 | Gabriel Halvarsson | 6/6 | Review Dev technical notes;Review BA user journeys;Highlight exceptions, failures, or processes that could benefit from optimisation;Handoff to PM;Show where data is captured, stored and transferred between systems;Document the technical workflow, such as form submissions & redirects, of the current implementation | DEV;Sprint 1 | The workflow of Monday.com is quite simple as seen within the document provided. Some details: only three areas of direction, forms, results, and status redundant columns duplicated column name manually changing status through the back-end With the LLM-minded approach to the process, the direction will remain very similar but more automatic and streamlined. Handoff: PM (Gabriel) Task reviewed and marked as completed. -Gabriel
1vDqv56-XEmTRPNH-QnRWsgAGgsq | [Sprint 1 Week 3] - Elicit client requirement: 60 | Sprint 1 Week 3 |  | Completed | Medium | Anas Rizwan | Joel Waterhouse | 2026-09-07 | 2026-09-08 | 2026-09-07 |  | false | 2026-09-09 | Anas Rizwan | 4/4 | Review technical notes from Devs;Handoff to PM;Compare technical notes, client requirements, and current implementation;Create comprehensive notes on findings | BA;Sprint 1 | Handoff: PM (Gabriel) Task reviewed and marked as completed. - Gabriel
K81xw68Fkku3vZqBkMmTNMgAA8pk | [Sprint 1 Week 3] Create User Journeys: 120 | Sprint 1 Week 3 |  | Completed | Important | Anas Rizwan | Joel Waterhouse | 2026-09-07 | 2026-09-08 | 2026-09-07 |  | false | 2026-09-09 | Anas Rizwan | 4/4 | Review the client requirements;Create a user workflow;Handoff to UX;Create in-depth user stories for an accurate and precise user journey | BA;Sprint 1 | Handoff: UX (Diya)
V_dIahyRO06NP-1INqdVZcgADLof | [Sprint 1 Week 3] Review BA User Journey: 60 | Sprint 1 Week 3 |  | Completed | Medium | Diya Diljith | Joel Waterhouse | 2026-09-07 | 2026-09-08 | 2026-09-07 |  | false | 2026-09-09 | Gabriel Halvarsson | 4/4 | Create Notes for later wireframe construction;Analyse user journeys;Handoff to Dev 2 (Gabe);Access BA user journeys | UX;Sprint 1 | Git URL :https://github.com/Joel-Wat/Capstone-26-Team-2/blob/main/Sprint%201/UX/UX%20Artefacts/Readme.md Figma:https://www.figma.com/design/SMHt70rdFa1dILxWsd3Okr/user?node-id=0-1&p=f&t=h7yz006aRUzqmQhK-0 Handoff: Dev 2 (Gabe) Task reviewed and marked as completed -Gabriel
BbHuozjvRES_5BEYIlmiOMgAGwjr | [Sprint 1 Week 3] Post role tasks on planner: 60 | Sprint 1 Week 3 |  | Completed | Urgent | Joel Waterhouse | Joel Waterhouse | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-07 | Gabriel Halvarsson | 6/6 | Create and post tasks on planner;Handoff to PM (?);Allocate tasks to relevant roles;Based off of meeting, draw up tasks for the group to complete this week;Set due dates, & explicitly state handoffs;Notify group of new tasks | DEV;Sprint 1 | Tian was unavailable so Dev (Joel Waterhouse) took responsibility. During teams meeting, Gabriel, Diya, and Joel discussed week 3 workload and deliverables. Will communicate with Alessio accordingly. This task was completed before the PM swap was decided in the catchup with Alessio, in future sprints Gabriel will be responsible for task creation and allocation. Handoff: PM (Gabriel) Task reviewed and marked as completed. If more tasks emerge during this sprint, the planner will be updated accordingly. - Gabriel
eD49TXTcyU61oiEpkZBe_8gAJTvd | [Sprint 1 Week 3] Construction of Wireframes: 180 | Sprint 1 Week 3 |  | Completed | Important | Diya Diljith | Joel Waterhouse | 2026-09-07 | 2026-09-09 | 2026-09-07 |  | false | 2026-09-08 | Diya Diljith | 4/4 | Create rough mock up;Submit Design to BA;Review Notes created on the user journeys;Go back to the notes then create a more detailed design | UX;Sprint 1 | Done:Reviewed the user journey and completedd refined UX designs for the dynamic forms platform. Deliverable: Figma wireframes that covers dynamic form requests and the client results interface. Note for next role: BA -please review the refined designs against the user requirements and provide feedback. Git URL :https://github.com/Joel-Wat/Capstone-26-Team-2/tree/main/Sprint%201/UX/UX%20Artefacts Figma:https://www.figma.com/design/kpd3Xetg710lrMz9sOQBBe/UX-Wireframe?t=op1TdvYOrcbwOUKW-0
EbRVCTdhWEOb3smAyiXiIMgAILtr | [Sprint 1 Week 3] Review Wireframes: 60 | Sprint 1 Week 3 |  | Completed | Medium | Anas Rizwan | Joel Waterhouse | 2026-09-07 | 2026-09-09 | 2026-09-07 |  | false | 2026-09-09 | Gabriel Halvarsson | 3/3 | Create notes if need changes, if so, handoff to UX for fix;Handoff wireframes and notes to Dev 2 (Gabriel);Review Wireframes | BA;Sprint 1 | Handoff: Dev (Gabriel) Task reviewed and marked as completed -Gabriel
QJGh-1zxsUS32J2bDrBqdcgAL_Sl | [Sprint 1 Week 3] Book meeting for Sprint 1 Playback: 30 | Sprint 1 Week 3 |  | Completed | Medium | Gabriel Halvarsson | Joel Waterhouse | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-08 | Joel Waterhouse | 4/4 | Handoff to Dev 2 (Joel) for review;Create teams meeting with team to discuss availabilities;Discuss with group a suitable time to hold meeting;Create booking with Jolly | DEV;Sprint 1 | Handoff: Dev 2 (Joel)
WCKFmBTq_k67blmPPYiH98gAGCm7 | [Sprint 1 Week 3] Review and amend planner tasks: 60 | Sprint 1 Week 3 |  | Completed | Medium | Gabriel Halvarsson | Joel Waterhouse | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-08 | Joel Waterhouse | 3/3 | Confirm all checklists, dates, roles, priorities exist and are correct;Review all tasks created for sprint 1 week 3;Receive tasks handed off by Dev 2 (Joel) | DEV;Sprint 1
DBGxI3D5BESUpXGx6hMescgANvFD | [Sprint 1 Week 3] Create Sprint Playback Slide Deck: 120 | Sprint 1 Week 3 |  | Completed | Important | Gabriel Halvarsson | Joel Waterhouse | 2026-09-07 | 2026-09-10 | 2026-09-07 |  | false | 2026-09-11 | Gabriel Halvarsson | 4/4 | Create a slide deck;Curate and read through all of sprint 1's artefacts;Prepare speaker notes;Time presentation and ensure it is shorter than seven minutes | DEV;Sprint 1 | Task completed, moving to done. -Gabriel Reason for late completion: Sprint playback was today, slide deck was completed in time but not marked as completed on the planner. Lots on my plate to organise this week, still lots to curate and submit for progress 3/9 submission. Previous PM was very disorganised and it is taking a lot of effort to clean things up.
_fiClMj990qwzniwH-V1LMgAEzfP | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | Sprint 1 Week 3 |  | Completed | Medium | Gabriel Halvarsson | Gabriel Halvarsson | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | Gabriel Halvarsson | 4/4 | Review group contributions, prompt members to complete tasks if needed;Put together documents for submission on Sunday;Add contributions to Master Document;Add artefacts to GitHub repo | DEV;Sprint 1 | This task is a duplicate for each group member.
BKAgCjpk-k-olSLGuvK4aMgAPOyR | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | Sprint 1 Week 3 |  | Completed | Medium | Joel Waterhouse | Gabriel Halvarsson | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | Gabriel Halvarsson | 4/4 | Review group contributions, prompt members to complete tasks if needed;Add artefacts to GitHub repo;Put together documents for submission on Sunday;Add contributions to Master Document | DEV;Sprint 1 | This task is a duplicate for each group member.
EDe-bH1C60yqoIYhZ3epj8gAKPBL | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | Sprint 1 Week 3 |  | Completed | Medium | Anas Rizwan | Gabriel Halvarsson | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | Gabriel Halvarsson | 4/4 | Review group contributions, prompt members to complete tasks if needed;Add contributions to Master Document;Add artefacts to GitHub repo;Put together documents for submission on Sunday | BA;Sprint 1 | This task is a duplicate for each group member.
FRJhswoOrUGlGFA-4QL1S8gAPC_F | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | Sprint 1 Week 3 |  | Completed | Medium | Diya Diljith | Gabriel Halvarsson | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | Gabriel Halvarsson | 4/4 | Add artefacts to GitHub repo;Put together documents for submission on Sunday;Review group contributions, prompt members to complete tasks if needed;Add contributions to Master Document | UX;Sprint 1 | This task is a duplicate for each team member.
OAs_Rr8bYUOPZ1WSs9UN4sgAJPHa | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | Backlog |  | Not started | Medium | Tianxiang Hang | Gabriel Halvarsson | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false |  |  | 0/5 | Add artefacts to GitHub repo;Ensure all existing artefacts from previous weeks are in the repo;Review group contributions, prompt members to complete tasks if needed;Put together documents for submission on Sunday;Add contributions to Master Document | PM;Sprint 1 | This task is a duplicate for each team member.
wnc5ZVST4Eav1xXpA4UVbcgAP_tT | [Sprint 1 Week 3] Create User Personas: 120 | Sprint 1 Week 3 |  | Completed | Important | Diya Diljith | Gabriel Halvarsson | 2026-09-09 | 2026-09-10 | 2026-09-07 |  | false | 2026-09-10 | Diya Diljith | 5/5 | Create 1–3 detailed personas that cover the main user types relevant to the project;Identify key user groups, needs, behaviours, goals, and pain points from available project research;Review and finalise personas;Handoff to PM for sprint playback slide deck;Include context, goals, motivations, pain points, behaviours, and needs | UX;Sprint 1 | Handoff: PM Task reviewed and marked as completed. - Gabriel Reason for moving task late: Sprint playback was today, several tasks were not managed on the planner in a timely manner. Trying to learn and pick up the duties of the previous PM in the span of a week has put a lot on my plate.
Ys2Zphk3oUqUt06hxydQMcgAFg9k | [Sprint 1 Week 3] Refine User Journeys: 60 | Sprint 1 Week 3 |  | Completed | Important | Anas Rizwan | Gabriel Halvarsson | 2026-09-09 | 2026-09-10 | 2026-09-07 |  | false | 2026-09-10 | Anas Rizwan | 5/5 | Review UX personas and key scenarios;Handoff to PM;Document the steps each persona takes in order to complete their goals;Validate and finalise user journeys;Define user actions, system interactions, decisions, pain points, dependencies, and requirements | BA;Sprint 1 | Handoff: PM Task reviewed and marked as completed. -Gabriel

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
-kEG1Tw5QEq1HHQtU_SP2cgAHzYq | Labels | xLPApfbhckqE8lFSrDU9UMgAD0GX |  | Not started | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false
QSNHFzIY10qLVtJOZgBi7sgAB-Ov | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-14 | 1abf4005-726a-43db-9542-505ee9215a04 | 4/5 | Edge cases documented;Login scope explicitly stated as styling-only;Document updated;Team page fields listed with validation/display rules;Requirements shared with PM and UX | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Login Restyling.docx
iXpQpvrZFUum7UVNVVMRDMgACx9R | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-15 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 5/5 | Visual consistency between the two checked;Team page mockup complete;Login page mockup complete;Design shared with BA for validation;Document Updated | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task documentDocument.docx
VYcC9FH77UmvYSYtuMYj3cgAKN3_ | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 5/5 | Design formally approved;Login scope confirmed unchanged;Every required field checked against the design;Gaps (if any) sent back to UX and resolved;Document Updated | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx
iiLGTM8HakKeTcdPq6tAHMgAKslD | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 4/4 | Visual style matches approved mockup;No authentication logic changed;Existing login validation/errors still function as before;Update document | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. Update master document.
zgPuuIxcbEGc8USZQpwqMMgAB9en | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0;6298b12a-dfa6-4613-91a2-6b30990cfde0 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 4/4 | Document updated;Team page renders per design with all required fields;Team page not directly accessible without login;Successful login redirects to team page | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update master document.
8IiRF3sthUCIj2fqQUgI8sgAF08p | [BOOTSTRAP RESTYLING] - Deploy - 120 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 0/4 | Live URL loads without errors;Login → redirect → team page flow spot-checked on the deployed URL;Deployment completed via boilerplate pipeline;Document updated | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc
5Ljn_w-nBUSNwqHXp_9ut8gACRdu | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 4/4 | Valid login tested end-to-end on deployed URL;Document updated;All required content verified correct and complete;Redirect to team page confirmed | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document
Se9IJ_trqEWlOQxtymn9a8gAB8Lc | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 0/5 | Direct team-page access without login tested (must redirect);Update Document;Bugs logged with repro steps, or none-found confirmed;Missing-photo and long-blurb edge cases tested;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc
5udzOSOE-k6Uaon_24tvIsgAA7Yd | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | vOkagFF0OUic45j3OmrDAcgAIf2g |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-07 |  |  |  | false | 2026-08-16 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 3/3 | Feature reviewed end-to-end against requirements and design;All prior tasks' checklists verified complete;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off
Enz164Azd0iytZ2s-qU-TsgAD7U6 | Individual Data review - Dev | T5h4tp9EWE2EsrwSmb90hsgALrdn |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-16 |  |  |  | false | 2026-08-29 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 3/3 | Notes added to the shared document in a format the team can use for synthesis;Master document updated;Recurring pain points identified and logged | DEV | Monday.com review with focus on technical lens.
qFwEnBVd0EWNyiLLAImZEcgAFUAu | Individual Data review - Dev | T5h4tp9EWE2EsrwSmb90hsgALrdn |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-16 |  |  |  | false | 2026-08-29 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2/2 | Recurring pain points identified and logged;Notes added to the shared document in a format the team can use for synthesis | DEV | Monday.com review with focus on technical lens.
fWB-j6qaWUG3MVzTxa-Ny8gABguJ | Final Synthesis and review | T5h4tp9EWE2EsrwSmb90hsgALrdn |  | Completed | Medium |  | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-16 |  |  |  | false | 2026-08-29 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 0/2 | Clear statement of what "success" means for this project;Ready to inform Sprint 2 solution decisions | PM | Converge Week 1-2 findings into a clear articulation of what a successful outcome looks like, informing sprint 2 planning. PM should produce a final write up
e9NpoS1ad0C9M60modzDq8gANoPg | Explore technical feasibilities of Proposed solutions during Tech dropin | T5h4tp9EWE2EsrwSmb90hsgALrdn |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0;6298b12a-dfa6-4613-91a2-6b30990cfde0 | 51ba8739-ac3f-4e32-a92a-e0434684a93c | 2026-08-25 |  |  |  | false | 2026-08-30 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 4/4 | Identify which LLM providers/APIs fit the project best;Check cost/privacy implications of LLM integration;Summarize feasibility findings;Review tech advisor's proposed LLM integration approach | DEV | Assess the technical feasibility of integrating an LLM into the platform, as proposed by the tech advisor
F3cBqLuKAUOdB1C0c1SwwMgAOSnm | [Sprint 1 Week 3] - Create a shared GitHub repository: 120 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-07 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Create folder hierachy for each sprint, role, artefacts, etc.;ReadMe - Completion;Set up Github Actions;Handoff to Dev 1 (Gabriel) | DEV;Sprint 1 | Handoff: Dev (Gabriel) Task reviewed and marked as completed - Gabriel
YErLUw2HaUeBcCOq9fIZesgAKi9q | [Sprint 1 Week 3] - Create technical workflow of the current implementation: 120 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-12 | 2026-09-07 |  | false | 2026-09-11 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 6/6 | Review Dev technical notes;Review BA user journeys;Highlight exceptions, failures, or processes that could benefit from optimisation;Handoff to PM;Show where data is captured, stored and transferred between systems;Document the technical workflow, such as form submissions & redirects, of the current implementation | DEV;Sprint 1 | The workflow of Monday.com is quite simple as seen within the document provided. Some details: only three areas of direction, forms, results, and status redundant columns duplicated column name manually changing status through the back-end With the LLM-minded approach to the process, the direction will remain very similar but more automatic and streamlined. Handoff: PM (Gabriel) Task reviewed and marked as completed. -Gabriel
1vDqv56-XEmTRPNH-QnRWsgAGgsq | [Sprint 1 Week 3] - Elicit client requirement: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 1abf4005-726a-43db-9542-505ee9215a04 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-08 | 2026-09-07 |  | false | 2026-09-09 | 1abf4005-726a-43db-9542-505ee9215a04 | 4/4 | Review technical notes from Devs;Handoff to PM;Compare technical notes, client requirements, and current implementation;Create comprehensive notes on findings | BA;Sprint 1 | Handoff: PM (Gabriel) Task reviewed and marked as completed. - Gabriel
K81xw68Fkku3vZqBkMmTNMgAA8pk | [Sprint 1 Week 3] Create User Journeys: 120 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Important | 1abf4005-726a-43db-9542-505ee9215a04 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-08 | 2026-09-07 |  | false | 2026-09-09 | 1abf4005-726a-43db-9542-505ee9215a04 | 4/4 | Review the client requirements;Create a user workflow;Handoff to UX;Create in-depth user stories for an accurate and precise user journey | BA;Sprint 1 | Handoff: UX (Diya)
V_dIahyRO06NP-1INqdVZcgADLof | [Sprint 1 Week 3] Review BA User Journey: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 858abc41-625d-4458-8b9f-a122e6363da4 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-08 | 2026-09-07 |  | false | 2026-09-09 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Create Notes for later wireframe construction;Analyse user journeys;Handoff to Dev 2 (Gabe);Access BA user journeys | UX;Sprint 1 | Git URL :https://github.com/Joel-Wat/Capstone-26-Team-2/blob/main/Sprint%201/UX/UX%20Artefacts/Readme.md Figma:https://www.figma.com/design/SMHt70rdFa1dILxWsd3Okr/user?node-id=0-1&p=f&t=h7yz006aRUzqmQhK-0 Handoff: Dev 2 (Gabe) Task reviewed and marked as completed -Gabriel
BbHuozjvRES_5BEYIlmiOMgAGwjr | [Sprint 1 Week 3] Post role tasks on planner: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Urgent | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-07 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 6/6 | Create and post tasks on planner;Handoff to PM (?);Allocate tasks to relevant roles;Based off of meeting, draw up tasks for the group to complete this week;Set due dates, & explicitly state handoffs;Notify group of new tasks | DEV;Sprint 1 | Tian was unavailable so Dev (Joel Waterhouse) took responsibility. During teams meeting, Gabriel, Diya, and Joel discussed week 3 workload and deliverables. Will communicate with Alessio accordingly. This task was completed before the PM swap was decided in the catchup with Alessio, in future sprints Gabriel will be responsible for task creation and allocation. Handoff: PM (Gabriel) Task reviewed and marked as completed. If more tasks emerge during this sprint, the planner will be updated accordingly. - Gabriel
eD49TXTcyU61oiEpkZBe_8gAJTvd | [Sprint 1 Week 3] Construction of Wireframes: 180 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Important | 858abc41-625d-4458-8b9f-a122e6363da4 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-09 | 2026-09-07 |  | false | 2026-09-08 | 858abc41-625d-4458-8b9f-a122e6363da4 | 4/4 | Create rough mock up;Submit Design to BA;Review Notes created on the user journeys;Go back to the notes then create a more detailed design | UX;Sprint 1 | Done:Reviewed the user journey and completedd refined UX designs for the dynamic forms platform. Deliverable: Figma wireframes that covers dynamic form requests and the client results interface. Note for next role: BA -please review the refined designs against the user requirements and provide feedback. Git URL :https://github.com/Joel-Wat/Capstone-26-Team-2/tree/main/Sprint%201/UX/UX%20Artefacts Figma:https://www.figma.com/design/kpd3Xetg710lrMz9sOQBBe/UX-Wireframe?t=op1TdvYOrcbwOUKW-0
EbRVCTdhWEOb3smAyiXiIMgAILtr | [Sprint 1 Week 3] Review Wireframes: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 1abf4005-726a-43db-9542-505ee9215a04 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-09 | 2026-09-07 |  | false | 2026-09-09 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 3/3 | Create notes if need changes, if so, handoff to UX for fix;Handoff wireframes and notes to Dev 2 (Gabriel);Review Wireframes | BA;Sprint 1 | Handoff: Dev (Gabriel) Task reviewed and marked as completed -Gabriel
QJGh-1zxsUS32J2bDrBqdcgAL_Sl | [Sprint 1 Week 3] Book meeting for Sprint 1 Playback: 30 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-08 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 4/4 | Handoff to Dev 2 (Joel) for review;Create teams meeting with team to discuss availabilities;Discuss with group a suitable time to hold meeting;Create booking with Jolly | DEV;Sprint 1 | Handoff: Dev 2 (Joel)
WCKFmBTq_k67blmPPYiH98gAGCm7 | [Sprint 1 Week 3] Review and amend planner tasks: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-07 | 2026-09-07 |  | false | 2026-09-08 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 3/3 | Confirm all checklists, dates, roles, priorities exist and are correct;Review all tasks created for sprint 1 week 3;Receive tasks handed off by Dev 2 (Joel) | DEV;Sprint 1
DBGxI3D5BESUpXGx6hMescgANvFD | [Sprint 1 Week 3] Create Sprint Playback Slide Deck: 120 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Important | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | 2026-09-07 | 2026-09-10 | 2026-09-07 |  | false | 2026-09-11 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Create a slide deck;Curate and read through all of sprint 1's artefacts;Prepare speaker notes;Time presentation and ensure it is shorter than seven minutes | DEV;Sprint 1 | Task completed, moving to done. -Gabriel Reason for late completion: Sprint playback was today, slide deck was completed in time but not marked as completed on the planner. Lots on my plate to organise this week, still lots to curate and submit for progress 3/9 submission. Previous PM was very disorganised and it is taking a lot of effort to clean things up.
_fiClMj990qwzniwH-V1LMgAEzfP | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Review group contributions, prompt members to complete tasks if needed;Put together documents for submission on Sunday;Add contributions to Master Document;Add artefacts to GitHub repo | DEV;Sprint 1 | This task is a duplicate for each group member.
BKAgCjpk-k-olSLGuvK4aMgAPOyR | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 6298b12a-dfa6-4613-91a2-6b30990cfde0 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Review group contributions, prompt members to complete tasks if needed;Add artefacts to GitHub repo;Put together documents for submission on Sunday;Add contributions to Master Document | DEV;Sprint 1 | This task is a duplicate for each group member.
EDe-bH1C60yqoIYhZ3epj8gAKPBL | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 1abf4005-726a-43db-9542-505ee9215a04 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Review group contributions, prompt members to complete tasks if needed;Add contributions to Master Document;Add artefacts to GitHub repo;Put together documents for submission on Sunday | BA;Sprint 1 | This task is a duplicate for each group member.
FRJhswoOrUGlGFA-4QL1S8gAPC_F | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Medium | 858abc41-625d-4458-8b9f-a122e6363da4 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false | 2026-09-13 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 4/4 | Add artefacts to GitHub repo;Put together documents for submission on Sunday;Review group contributions, prompt members to complete tasks if needed;Add contributions to Master Document | UX;Sprint 1 | This task is a duplicate for each team member.
OAs_Rr8bYUOPZ1WSs9UN4sgAJPHa | [Sprint 1 Week 3] Individual contribution to Project Progress 3/9 submission: 60 | SesDxeGyakGZizmwlJnAnMgAE74e |  | Not started | Medium | 51ba8739-ac3f-4e32-a92a-e0434684a93c | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-08 | 2026-09-13 | 2026-09-11 |  | false |  |  | 0/5 | Add artefacts to GitHub repo;Ensure all existing artefacts from previous weeks are in the repo;Review group contributions, prompt members to complete tasks if needed;Put together documents for submission on Sunday;Add contributions to Master Document | PM;Sprint 1 | This task is a duplicate for each team member.
wnc5ZVST4Eav1xXpA4UVbcgAP_tT | [Sprint 1 Week 3] Create User Personas: 120 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Important | 858abc41-625d-4458-8b9f-a122e6363da4 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-09 | 2026-09-10 | 2026-09-07 |  | false | 2026-09-10 | 858abc41-625d-4458-8b9f-a122e6363da4 | 5/5 | Create 1–3 detailed personas that cover the main user types relevant to the project;Identify key user groups, needs, behaviours, goals, and pain points from available project research;Review and finalise personas;Handoff to PM for sprint playback slide deck;Include context, goals, motivations, pain points, behaviours, and needs | UX;Sprint 1 | Handoff: PM Task reviewed and marked as completed. - Gabriel Reason for moving task late: Sprint playback was today, several tasks were not managed on the planner in a timely manner. Trying to learn and pick up the duties of the previous PM in the span of a week has put a lot on my plate.
Ys2Zphk3oUqUt06hxydQMcgAFg9k | [Sprint 1 Week 3] Refine User Journeys: 60 | YNWUrPzKVk28bYKEWG6a28gALNGY |  | Completed | Important | 1abf4005-726a-43db-9542-505ee9215a04 | cb238b28-4bcf-4435-86d0-5d03875dfeb0 | 2026-09-09 | 2026-09-10 | 2026-09-07 |  | false | 2026-09-10 | 1abf4005-726a-43db-9542-505ee9215a04 | 5/5 | Review UX personas and key scenarios;Handoff to PM;Document the steps each persona takes in order to complete their goals;Validate and finalise user journeys;Define user actions, system interactions, decisions, pain points, dependencies, and requirements | BA;Sprint 1 | Handoff: PM Task reviewed and marked as completed. -Gabriel

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
2GXFzqrfUk2zz0OERNr0xMgAMX3g | Blocked
xLPApfbhckqE8lFSrDU9UMgAD0GX | Documents & Updates
SesDxeGyakGZizmwlJnAnMgAE74e | Backlog
AcXeXgYbdkar9Aa3WuODAcgAFtwT | Doing
-qXzVkkdZEOFlUMAF5jkxMgAJufR | Reviewing
LHE0OLye0kaeGOl_scKm-sgAJVXN | Done
x-VoagUpkUmqwpnKhg1LI8gAI5rQ | Testing
y61TUGOfokefO1tgu0-waMgAC6gJ | Done
3P6tTkQdmk6bnhZT8ipJCsgAO3C5 | Clean up
vOkagFF0OUic45j3OmrDAcgAIf2g | Sprint 0
3DgB9Fx8VUe_wkK4eLk0YsgAGsKO | Sprint 1 Week 1
T5h4tp9EWE2EsrwSmb90hsgALrdn | Sprint 1 Week 2
YNWUrPzKVk28bYKEWG6a28gALNGY | Sprint 1 Week 3

## Users
User ID | User Name | Email
51ba8739-ac3f-4e32-a92a-e0434684a93c | Tianxiang Hang | S4101441@student.rmit.edu.au
1abf4005-726a-43db-9542-505ee9215a04 | Anas Rizwan | S4094686@student.rmit.edu.au
cb238b28-4bcf-4435-86d0-5d03875dfeb0 | Gabriel Halvarsson | S3849019@student.rmit.edu.au
6298b12a-dfa6-4613-91a2-6b30990cfde0 | Joel Waterhouse | S4094140@student.rmit.edu.au
858abc41-625d-4458-8b9f-a122e6363da4 | Diya Diljith | S4051716@student.rmit.edu.au